## Sheet1
Project Logbook
This logbook shows the record of all the events during the realization of the PSS_ACU project.
| Team members: | · Guillermo Hernández Ramírez
· Antonio Vázquez Tovar
· Habib Alejandro Apez González
| Coach: | Luis Martínez Villanueva
| Lastest update: | 2017-12-11
Start Date | Finish Date | Member | Activity
2017-12-04 | 2017-12-04 | Habib Apez | Git Hub repository creation.
2017-12-04 | 2017-12-04 | Habib Apez | Creation of the project frame based on previous projects.
2017-12-04 | 2017-12-05 | Team | Project Specifications analysis.
2017-12-04 | 2017-12-05 | Antonio Vázquez | Requirements analysis and its definition in the traceability matrix (Seat Belt Driver-Driver).
2017-12-04 | 2017-12-04 | Antonio Vázquez | Initial approach to the CAN Analyzer Tool from Microchip.
2017-12-04 | 2017-12-05 | Guillermo Hernández | Requirements analysis its definition in the traceability matrix (Seat Belt Reminder-Passenger).
2017-12-04 | 2017-12-05 | Habib Apez | Requirements analysis its definition in the traceability matrix (DIC Manager and Passenger Occupancy Manger).
2017-12-05 | 2017-12-05 | Team & coach | Meeting to redefine the project scope.
2017-12-05 | 2017-12-05 | Habib Apez | New Traceability matrix template which includes the review columns.
2017-12-05 | 2017-12-05 | Habib Apez | Creation of the Requirements Review document.
2017-12-06 | 2017-12-06 | Antonio Vázquez | Material acquired for the project develop (resistors, diodes, voltage converter).
2017-12-06 | 2017-12-06 | Habib Apez | Hands-on approach to the CAN Analyzer Tool from Microchip using the example CAN code provided by the coach.
2017-12-06 | 2017-12-06 | Team & coach | Meeting to clarify ambiguous requirements in the MIC Manager module and Passenger Occupancy Manager module specifications.
2017-12-07 | 2017-12-07 | Antonio Vázquez | Functional and Non-Functional delimitation into the Traceability matrix.
2017-12-07 | 2017-12-07 | Antonio Vázquez | UML diagrams created for the ACU’s State Machine, the Seat Belt Reminder Driver State Machine and the Use case for the Architecture diagram.
2017-12-07 | 2017-12-07 | Antonio Vázquez | DSD_Design Draft Document first approach and version.
2017-12-07 | 2017-12-07 | Guillermo Hernández | UML diagram created for the Seat Belt Reminder Passenger State Machine
2017-12-07 | 2017-12-07 | Guillermo Hernández | Comments on Seat Belt Reminder Passenger Requirements
2017-12-07 | 2017-12-07 | Guillermo Hernández | Add Seat Belt Reminder Passenger State Machine to DSD_Design Document
2017-12-07 | 2017-12-07 | Habib Apez | State Diagram of the Passanger Ocuppancy Manager module in ArgoUML
2017-12-07 | 2017-12-08 | Habib Apez | Develop of the ADC driver (MCAL, HAL and APP layers).
2017-12-08 | 2017-12-09 | Habib Apez | Develop of the Seat Sensor Manger state machine code.
2017-12-08 | 2017-12-10 | Antonio Vázquez | Develop of the CAN driver (MCAL and HAL).
2017-12-09 | 2017-12-09 | Guillermo Hernández & Habib Apez | Definition of the scheduler (tasks and periods) based on the requierements and system behaviour
2017-12-09 | 2017-12-09 | Habib Apez | Develop of the scheduler code
2017-12-09 | 2017-12-09 | Guillermo Hernández & Habib Apez | Timing testing for the scheduler using the Log Signal Analyzer
2017-12-09 | 2017-12-10 | Habib Apez | Timing testing for the Seat Sensor Manger with the scheduler using the Logic Signal Analyzer
2017-12-10 | 2017-12-10 | Habib Apez | Test Plan template created and fixed
2017-12-10 | 2017-12-10 | Habib Apez | Code compatibiity and folder structure issues fixed
2017-12-11 | 2017-12-11 | Habib Apez | SW_C_Code_Review document created and updated
2017-12-11 | 2017-12-11 | Habib Apez | Defect Log document created and updated
2017-12-11 | 2017-12-11 | Habib Apez | DSD_Design updated
2017-12-11 | 2017-12-12 | Habib Apez | Develop of an alternative CAN driver (MCAL and HAL).
2017-12-11 | 2017-12-11 | Guillermo Hernández | Traceability Matrix updated: comments added to requierements that will not be implemeted and word-standarization in the matrix.
2017-12-12 | 2017-12-12 | Guillermo Hernández & Habib Apez | Timing testing for the Read CAN bus function with the scheduler using the Logic Signal Analyzer
2017-12-12 | 2017-12-12 | Guillermo Hernández & Habib Apez | Problem with the CAN Analyzer from Microchip identified and solved
2017-12-12 | 2017-12-12 | Guillermo Hernández & Habib Apez | Connection between two NXP boards using the CAN bus to solve the CAN Analyzer issue found
2017-12-12 | 2017-12-12 | Antonio Vázquez | Develop ord the main State Machine of the ACU
2017-12-12 | OPEN | Antonio Vázquez | Develop of the Driver Seat Bealt Reminder State Machine
2017-12-13 | OPEN | Guillermo Hernández | Develop of the Passenger Seat Bealt Reminder State Machine
2017-12-13 | 2017-12-13 | Habib Apez | Realization constraints and targets added to the DSD_Design, CAN messages and signals description.
2017-12-13 | 2017-12-13 | Habib Apez | Test Plan updated, 10 Tests added
2017-12-13 | 2017-12-13 | Antonio Vázquez | CAN alternative driver validation and integration.