## Defect logs
Project: AEP_PSS_ACU
Proyect/Task | date | ID | Type | inyected | removed | Counter | Problem description | Solution description | Additional Information
AEP_PSS_ACU / Project scope analysis | 2017-12-05 | DEF_01 | Documentation | Requirements Analysis | Requirements Analysis | 1 | The current project scope is too challenging (considering the project deadline) and implies a large number requirements (at least 300). | The project scope can be reduced in order to accomplish the project but it shall show all the phases of the software development process. The team should decide which modules are going to be implemented based on its scopes and on the time frame given. | See Requierements Review document
AEP_PSS_ACU / Requierements analysis | 2017-12-06 | DEF_02 | Documentation | Requirements Analysis | Requirements Analysis | 2 | Some requierements are unclear / missing information | A meeting with the stakeholder was hold. | See Requierements Review document
AEP_PSS_ACU / Coding | 2017-12-09 | DEF_03 | Environment | Implementation | Implementation | 1 | Linker problem after compiling in S32 Studio. | Settings of the Cross ARM C++ Linker modified. | Solution found here: https://community.nxp.com/thread/353119#comment-507840
Note on E3: uids7089: Type of defect Use the next tab to identify the correct classification
Note on F3: uids7089: phase where the issue is Inyected: Requirements Design Implementation
Note on G3: uids7089: phase where the issue is removed: Desing Desing review Code Code Review Module Validation Sw Verification
Note on H3: uids7089: if the same issue is found more that once, increment the conuter

## Types of defects
Type | Description
Documentation | comments, messages
Syntax | spelling, punctuation, typos, instruction formats
Build, package | change management, library, version control
Assignment | declaration, duplicate names, scope, limits
Interface | procedure calls and reference, I/O, user formats
Checking | error messages, inadequate checks
Data | structure, content
Function | logic, pointers, loops, recursion, computation, function defects
System | configuration, timing, memory
Environment | design, compile, test, or other support system problems